CSE470 - Software Engineering

Crypto World Bank: Agile Development Methodology

Course: CSE470 - Software Engineering

Project: Decentralized Crypto Reserve & Lending Bank

Duration: 2 Months (8 Weeks)

Methodology: Agile/Scrum

Sprints: 3 Sprints

Date: February 2026

Authors: Md. Bokhtiar Rahman Juboraz (20301138) • Md. Mahir Ahnaf Ahmed (20301083)

Contents

| 1 | Project Overview |
| --- | --- |
| 2 | Sprint Structure |
| 3 | Sprint 1: Foundation & Core Banking |
| 4 | Sprint 2: Lending & Payment Features |
| 5 | Sprint 3: Advanced Features & Security |
| 6 | Agile Artifacts |
| 7 | Team Roles & Responsibilities |
| 8 | Risk Management |
| 9 | Metrics & KPIs |
| 10 | Communication Plan |
| 11 | SDLC Stage Mapping |
| 12 | Design Decisions and Alternatives Considered |
| 13 | UML and Architecture |
| 14 | Design Patterns |
| 15 | Software Testing and Metrics |
| 16 | Effort Estimation and Project Scheduling |
| 17 | Conclusion |

1. Project Overview

1.1 Project Scope

The Crypto World Bank is a decentralized lending platform built on blockchain technology with a hierarchical banking structure (World Bank → National Banks → Local Banks → Users). The system includes installment payments, AI/ML security layers, chat functionality, and comprehensive user management.

1.2 Development Methodology

Agile/Scrum Framework with the following characteristics:

• Sprint Duration: 2-3 weeks per sprint

• Team Size: 2 developers (thesis project)

• Weekly Sync: Progress review, blockers, planning (replaces daily standup for 2-person team)

• Sprint Planning: 1 hour at sprint start

• Sprint Review: 30 minutes at sprint end

• Retrospective: 30 minutes at sprint end

2. Sprint Structure

2.1 Overall Timeline

2.2 Sprint Breakdown

| Sprint | Duration | Focus Area | Key Deliverables |
| --- | --- | --- | --- |
| **Sprint 1** | Weeks 1-3 | Foundation & Core Banking | Smart contracts, basic UI, wallet integration, database schema |
| **Sprint 2** | Weeks 4-6 | Lending, Payment & Communication | Loan requests, installments, borrowing limits, chat, income verification, bank hierarchy |
| **Sprint 3** | Weeks 7-8 | AI/ML Security, Testing & Finalization | AI/ML integration, risk dashboard, profiles, market data, testing, documentation |

3. Sprint 1: Foundation & Core Banking

Duration: 3 Weeks (Weeks 1-3)

Sprint Goal: Establish core blockchain infrastructure and hierarchical banking structure

3.1 Sprint Backlog

Epic 1: Smart Contract Development (21 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-1.1 | World Bank contract — reserve management, national bank registration | 5 |
| US-1.2 | National Bank contract — borrow from WB, lend to Local Banks | 5 |
| US-1.3 | Local Bank contract — borrow from NB, lend to users | 5 |
| US-1.4 | Role-based access control — WB/NB/LB Admin, Bank User, Borrower | 3 |
| US-1.5 | Gas cost management — initiator pays; Polygon low-fee ($0.001–0.01/tx) | 3 |

Epic 2: Frontend Foundation (13 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-1.6 | Wallet connection — MetaMask, WalletConnect, Sepolia/Mumbai | 3 |
| US-1.7 | Dashboard UI — Material Design 3, responsive, blockchain-themed | 5 |
| US-1.8 | Navigation & layout — AppBar, role-based menu | 3 |
| US-1.9 | Blockchain visual elements — tx hash, security badges | 2 |

Epic 3: Database Schema (8 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-1.10 | Database design — 15 tables, 3NF (see CSE370) | 5 |
| US-1.11 | Migration scripts and seed data | 3 |

3.2 Sprint 1 Burndown

Total Story Points: 42

Team Velocity: ~21 points per week (estimated)

| Day | Planned | Completed | Remaining |
| --- | --- | --- | --- |
| Day 1 | 0 | 0 | 42 |
| Day 3 | 14 | 12 | 30 |
| Day 5 | 21 | 20 | 22 |
| Day 7 | 28 | 27 | 15 |
| Day 10 | 35 | 35 | 7 |
| Day 14 | 42 | 42 | 0 |

3.3 Sprint 1 Deliverables

• ✅ Smart contracts deployed on testnet

• ✅ Basic frontend with wallet connection

• ✅ Database schema implemented

• ✅ Role-based access control working

• ✅ Dashboard UI with blockchain elements

4. Sprint 2: Lending & Payment Features

Duration: 3 Weeks (Weeks 4-6)

Sprint Goal: Implement complete lending flow with installment payments and communication

4.1 Sprint Backlog

Epic 4: Loan Management (21 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-2.1 | Loan request — form, one per bank, on-chain storage | 5 |
| US-2.2 | Loan approval/rejection — pending view, approver per bank | 5 |
| US-2.3 | Income verification — file upload, document storage | 5 |
| US-2.4 | Borrowing limit — 6mo/1yr calc, 3+ paid exception | 5 |
| US-2.5 | Loan request visibility — hide after approval | 1 |

Epic 5: Installment Payment (13 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-2.6 | Installment logic — auto setup for ≥100 ETH, configurable count | 5 |
| US-2.7 | Installment UI — list, pay button, confirmation | 5 |
| US-2.8 | Deadline tracking — display, overdue warnings | 3 |

Epic 6: Chat System (13 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-2.9 | Borrower–bank chat — real-time, history, read/unread | 8 |
| US-2.10 | Chat notifications — in-app, unread count | 5 |

Epic 7: Profile Management (8 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-2.11 | Profile pages — all user types, role-specific | 5 |
| US-2.12 | Terms and conditions — view, acceptance tracking | 3 |

Epic 7b: QR Code System (3 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-2.13 | QR generation & scan — wallet, loan URL, contract address | 3 |

4.2 Sprint 2 Burndown

Total Story Points: 58

Team Velocity: ~27 points per week (estimated)

| Day | Planned | Completed | Remaining |
| --- | --- | --- | --- |
| Day 1 | 0 | 0 | 58 |
| Day 3 | 19 | 18 | 40 |
| Day 5 | 29 | 28 | 30 |
| Day 7 | 38 | 37 | 21 |
| Day 10 | 48 | 47 | 11 |
| Day 14 | 58 | 58 | 0 |

4.3 Sprint 2 Deliverables

• ✅ Complete loan request and approval system

• ✅ Installment payment functionality

• ✅ Deadline tracking in dashboard

• ✅ Chat system between borrowers and banks

• ✅ Profile pages for all user types

• ✅ Terms and conditions page

5. Sprint 3: Advanced Features & Security

Duration: 2 Weeks (Weeks 7-8)

Sprint Goal: Implement AI/ML security, market data visualization, AI chatbot, and finalize testing & documentation

5.1 Sprint Backlog

Epic 8: Market Data Visualization (8 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-3.1 | Market data API — CoinGecko/CoinMarketCap, caching | 3 |
| US-3.2 | Market value graph — Chart.js/Recharts, live + historical | 5 |

Epic 9: AI Chatbot (13 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-3.3 | Chatbot integration — NLP, context-aware responses | 5 |
| US-3.4 | Chatbot training — dataset, intent recognition | 5 |
| US-3.5 | Chatbot features — loan limit, payment, bank contact queries | 3 |

Epic 10: AI/ML Security Layer (21 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-3.6 | ML data collection — transaction logging, feature extraction | 5 |
| US-3.7 | Fraud detection model — risk scoring, loan approval integration | 8 |
| US-3.8 | Anomaly detection — alerts, dashboard | 5 |
| US-3.9 | Security logging — event tracking, bank dashboard | 3 |

Epic 11: Testing & QA (13 pts)

| ID | Story | Pts |
| --- | --- | --- |
| US-3.10 | Unit testing — smart contracts, >80% coverage | 5 |
| US-3.11 | Integration testing — E2E, API tests | 5 |
| US-3.12 | Security testing — contract audit, penetration testing | 3 |

5.2 Sprint 3 Burndown

Total Story Points: 55

Team Velocity: ~27 points per week (estimated)

| Day | Planned | Completed | Remaining |
| --- | --- | --- | --- |
| Day 1 | 0 | 0 | 55 |
| Day 3 | 18 | 17 | 38 |
| Day 5 | 27 | 26 | 29 |
| Day 7 | 36 | 35 | 20 |
| Day 10 | 45 | 44 | 11 |
| Day 14 | 55 | 55 | 0 |

5.3 Sprint 3 Deliverables

• ✅ Live cryptocurrency market data visualization

• ✅ AI chatbot for user support

• ✅ AI/ML security layer foundation

• ✅ Comprehensive testing suite

• ✅ Security audit completed

5.4 Integration, Testing & Deployment (Weeks 7-8)

These activities run in parallel with Sprint 3 development:

Integration Activities:

• Integrate all sprint deliverables

• Resolve integration issues

• Performance optimization

Testing Checklist:

•  Smart contract functionality (Hardhat unit tests)

•  Frontend-backend integration

•  Database operations (PostgreSQL)

•  Chat system real-time communication (WebSocket)

•  Installment payment flow (on-chain)

•  AI chatbot responses (NLP pipeline)

•  Market data updates (CoinGecko API + Redis cache)

•  Security layer monitoring (AI/ML risk scores)

•  Mobile responsiveness

•  Cross-browser compatibility

Deployment Activities:

• Deploy smart contracts to testnet (Polygon Mumbai / Ethereum Sepolia)

• Deploy frontend (Vercel free tier)

• Deploy backend API (Render free tier)

• Set up monitoring (application and blockchain event listeners)

Release Checklist:

•  All features implemented

•  All tests passing

•  Security audit completed

•  Documentation complete

•  Production deployment successful

•  Monitoring active

5.5 Sprint Story Points Distribution

5.6 Agile/Scrum Process Flow

6. Agile Artifacts

6.1 Product Backlog

The complete product backlog includes the condensed user stories (US-1.1 through US-3.12) from sections 3–5, plus additional items for future releases:

Future Features (Post-MVP):

• Multi-cryptocurrency support

• Advanced ML models (LSTM, Transformer)

• Mobile apps (iOS/Android)

• Internationalization (i18n)

• Advanced analytics dashboard

• Automated loan approval using ML

• Credit scoring system

6.2 Sprint Backlog

Each sprint has its own backlog (detailed in sections 3, 4, and 5).

6.3 Definition of Done

A user story is considered "Done" when:

• ✅ Code is written and reviewed

• ✅ Unit tests are written and passing

• ✅ Integration tests are passing

• ✅ Documentation is updated

• ✅ Code is merged to main branch

• ✅ Feature is deployed to staging

• ✅ Product Owner has accepted the story

6.4 Definition of Ready

A user story is "Ready" for sprint planning when:

• ✅ User story is clearly written

• ✅ Acceptance criteria are defined

• ✅ Story points are estimated

• ✅ Dependencies are identified

• ✅ Technical feasibility is confirmed

7. Team Roles & Responsibilities

7.1 Team Structure

This is a 2-person thesis project. Both members share responsibilities across all domains.

| Team Member | Primary Focus | Secondary Focus |
| --- | --- | --- |
| Md. Bokhtiar Rahman Juboraz (20301138) | Smart contract development, blockchain integration, backend API | AI/ML model development, documentation |
| Md. Mahir Ahnaf Ahmed (20301083) | Frontend development (React/TypeScript), UI/UX design | Database design, testing, documentation |

Supervisor: Mr. Annajiat Alim Rasel, Senior Lecturer, Dept. of CSE, Brac University

7.2 Collaboration Process

Weekly Sync Format:

1. What was completed this week?

2. What is planned for next week?

3. Are there any blockers or dependency issues?

Code Review: All pull requests reviewed by the other team member before merge.

8. Risk Management

8.1 Identified Risks

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Smart contract vulnerabilities | Medium | High | Security audit, extensive testing |
| Gas cost fluctuations | High | Medium | Gas optimization, cost estimation |
| ML model accuracy | Medium | Medium | Continuous training, human review |
| Integration complexity | Medium | High | Early integration, frequent testing |
| Scope creep | High | Medium | Strict sprint boundaries, backlog management |
| Team member unavailability | Low | High | Cross-training, documentation |

8.2 Risk Response Plan

• High Priority Risks: Weekly review and mitigation

• Medium Priority Risks: Bi-weekly review

• Low Priority Risks: Monthly review

9. Metrics & KPIs

9.1 Sprint Metrics

• Velocity: Story points completed per sprint

• Burndown: Progress tracking

• Sprint Goal Achievement: % of sprint goal met

9.2 Quality Metrics

• Test Coverage: > 80%

• Bug Density: < 5 bugs per 1000 lines of code

• Code Review Coverage: 100%

9.3 Performance Metrics

• Page Load Time: < 2 seconds

• Transaction Confirmation: < 30 seconds

• API Response Time: < 500ms

10. Communication Plan

10.1 Communication Channels

• Weekly Sync: Progress review, blockers, planning

• Sprint Planning: 1 hour, start of sprint

• Sprint Review: 30 minutes, end of sprint

• Retrospective: 30 minutes, end of sprint

• Supervisor Updates: Bi-weekly

10.2 Tools

• Version Control: GitHub (primary collaboration platform)

• Documentation: Overleaf (LaTeX report), Markdown files in repository

• Communication: In-person meetings, email (professor updates bi-weekly)

• IDE: VS Code with Cursor AI assistant

• CI/CD: GitHub Actions (planned)

11. SDLC Stage Mapping

The Agile sprint structure maps to the standard Software Development Life Cycle (SDLC) stages (ref: [GeeksforGeeks SDLC](https://www.geeksforgeeks.org/software-engineering/software-development-life-cycle-sdlc/)):

| SDLC Stage | Project Activity | Timeline |
| --- | --- | --- |
| 1. Planning & Requirements Analysis | Feasibility studies (technical, economic, operational, schedule); professor meetings; BCOLBD 2025 guideline review; stakeholder requirement gathering | Pre-Sprint |
| 2. Defining Requirements (SRS) | System analysis (CSE471); use case definitions (29 use cases); non-functional requirements; system constraints; user stories (US-1.x through US-3.x) | Pre-Sprint + Sprint 1 |
| 3. Designing Architecture | Three-layer architecture (Presentation, Smart Contract, Off-chain); database schema (15 tables, 3NF); component diagram; data flow diagram; ERD | Sprint 1 |
| 4. Development (Coding) | Smart contracts (Solidity), frontend (React/TypeScript), backend (FastAPI/Python), AI/ML models | Sprints 1–3 |
| 5. Testing | Hardhat unit tests (12+ tests); frontend integration tests; AI/ML model evaluation; end-to-end testing | Week 7 (Integration & Testing) |
| 6. Deployment | Testnet deployment (Polygon Mumbai / Ethereum Sepolia); frontend on Vercel; backend on Render | Week 8 (Release) |
| 7. Maintenance | Post-deployment monitoring; AI/ML model retraining; bug fixes; feature iteration | Post-Release |

12. Design Decisions and Alternatives Considered

Per professor requirement: *"For every decision you take, first present the alternative and then justify your first and second choices."*

The complete decision justification document is maintained in DECISION_JUSTIFICATION_PLAN.md. Summary:

| Decision Area | 1st Choice | 2nd Choice | Key Criterion |
| --- | --- | --- | --- |
| Development Methodology | Agile / Scrum | Incremental / Spiral | Evolving scope, sprint milestones |
| Software Architecture | DApp + Off-chain AI | Hybrid with Oracle | Gas cost, ML iteration flexibility |
| Frontend Framework | React + TypeScript | Vue + TypeScript | Web3 library ecosystem (Wagmi, RainbowKit) |
| Smart Contract Platform | Ethereum / EVM (Solidity) | Solana (Rust) | Largest ecosystem, free testnets, OpenZeppelin |
| UI Design System | Material Design 3 (MUI) | Tailwind CSS | Professional banking UI, development speed |
| Release Cycle | Incremental releases | Continuous deployment | Professor milestones, integration risk |
| Fraud Detection Algorithm | Random Forest | XGBoost | SHAP compatibility, 94%+ precision |
| Anomaly Detection | Isolation Forest | Autoencoder | Unsupervised, no labeled data needed |
| XAI Method | SHAP | LIME | Theoretical foundation, regulatory compliance |
| Database | PostgreSQL | SQLite | CSE370 alignment, 3NF schema, async support |
| Hosting / Deployment | Vercel + Render | Localhost | $0 cost, public URL, CI/CD |

Each decision includes 2–3 alternatives evaluated, the chosen option with justification, and a backup option with rationale for when it would be preferred. See DECISION_JUSTIFICATION_PLAN.md for full details including criteria analysis.

13. UML and Architecture

13.1 Use Case Diagram

The Use Case diagram is maintained in the CSE471 report. See [Usecase diagram.png](https://github.com/Yuvraajrahman/Cryto-World-Bank/blob/main/Documentation/Diagrams/CSE471/Usecase%20diagram.png) and [CSE471 System Analysis Report §4 Use Case Diagram](https://github.com/Yuvraajrahman/Cryto-World-Bank/blob/main/Documentation/CSE471_SYSTEM_ANALYSIS_AND_DESIGN%20REPORT.md#4-use-case-diagram). It shows actors (Borrower, Bank User, World Bank, National Bank, Local Bank) and 29 use cases.

13.2 Class Diagram (Conceptual)

| Component | Classes / Modules |
| --- | --- |
| Frontend | `App`, `Layout`, `Pages` (Dashboard, Loan, Deposit, Chat, Profile), `Hooks` (useContract, useUser) |
| Backend | `routes` (loans, users, blockchain), `services` (blockchain), `database` |
| Smart Contracts | WorldBankReserve, NationalBank, LocalBank (Solidity) |
| ML Backend | fraud_detector, anomaly_detector, XAI (SHAP) |

Relationships: Frontend → Backend API; Backend → PostgreSQL, Blockchain; Backend → ML API for risk scoring.

13.3 Software Architecture: MVC and Layered

• MVC: React components = View; hooks/state = Controller logic; backend API + DB = Model.

• Layered: Presentation (React) → Application (Node.js/FastAPI) → Data (PostgreSQL, blockchain).

• Client-Server: Frontend (client) ↔ Backend (server); Backend ↔ Blockchain nodes.

14. Design Patterns

| Pattern | Usage |
| --- | --- |
| Singleton | Contract instances (useContract), Wagmi/Web3 config — single shared instance |
| Observer | React state, blockchain event listeners — components react to data changes |
| Adapter | Wagmi/viem adapts different wallet providers (MetaMask, WalletConnect) to a common interface |

15. Software Testing and Metrics

15.1 Testing

• Unit tests: Hardhat for smart contracts; Jest/Vitest for frontend/backend (planned).

• Integration: API tests, E2E (Playwright/Cypress) for critical flows.

15.2 Software Metrics

| Metric | Target | Notes |
| --- | --- | --- |
| Cyclomatic Complexity | < 10 per function | Reduces branching; complex logic split into smaller functions |
| CFG (Control Flow Graph) | Used for test path coverage | Each branch in conditionals adds paths |
| Test Coverage | > 80% | Smart contracts; frontend/backend in progress |

16. Effort Estimation and Project Scheduling

16.1 COCOMO (Simplified)

• Mode: Organic (small team, familiar domain).

• Size: ~15–20 KLOC (frontend + backend + contracts + ML).

• Effort: E = a × (KLOC)^b; a=2.4, b=1.05 → ~35–45 person-months nominal; scaled down for 2-person, 2-month → ~4 person-months equivalent for prethesis scope.

16.2 CPM (Critical Path Method)

Critical path: Smart Contracts → Wallet Integration → Loan Flow → AI/ML Integration → Testing. Longest dependency chain; delays here directly impact release. Non-critical: Market data, QR codes, profile polish can slip without blocking core delivery.

16.3 Refactoring

Refactoring is applied during sprint retrospectives: extract reusable hooks, consolidate API routes, simplify contract modifiers. No large-scale refactor planned; incremental improvements as technical debt is identified.

17 Prototype Demonstration: 
The following screenshots show the Crypto World Bank prototype in action:
Figure 1: Dashboard Overview

Figure 2: Lending Interface

Figure 3: Transaction & Chat

Figure 4: Profile & Settings

18. Conclusion

This Agile development plan provides a structured approach to building the Crypto World Bank platform over 2 months with 3 sprints (Prethesis 1 scope). The methodology ensures:

• Incremental delivery of features aligned with SDLC stages

• Continuous feedback and improvement through sprint reviews

• Risk mitigation through early testing and integration

• Justified design decisions with documented alternatives

• Quality assurance throughout development

The plan is flexible and can be adjusted based on team velocity and changing requirements.

Document Version: 3.1

Last Updated: February 2026

Author: Software Engineering Team

Course: CSE470 - Software Engineering